## Overview
Field | Value
Product | AfroSpice Owner Workspace
Scope | Owner-only retail operations workspace covering dashboard, assistant, settings, inventory command, POS, orders, refunds, customers, suppliers, user management, deployment smoke, and post-release monitoring.
Current seeded reference data | 50 products ¦ 8 suppliers ¦ 12 customers ¦ 7 users ¦ 16 sales
Primary release goal | Verify the app is production-ready for owner operations with correct routing, dark mode parity, POS checkout and receipt flow, refund approvals, settings persistence, notifications, deployment smoke, and assistant reliability.
Execution model | Use dropdown columns for Severity, Assigned To, and Status while executing UAT. Capture screenshots, script output, logs, and receipt evidence directly in the Evidence and Notes fields.
Critical flows | 1. Owner sign-in with PIN or Windows Hello 2. Dashboard and route action cards 3. Executive assistant question, follow-up, and navigation 4. Settings save, theme toggle, and notifications 5. POS search, pagination, sale, and print 6. Orders refund request and owner approval 7. Customer loyalty and checkout recognition 8. User management routes and staff records 9. Dark mode and zoom sweep 10. Backend health, readiness, and data quality 11. Deployment smoke and monitoring
Pass criteria | All P1 owner flows pass, release verification is green, no blocking dark-mode or routing defects remain, and deployment smoke plus monitoring checks are signed off.
Workbook usage | Core Test Cases = core owner UAT. Owner Deep Dive = full route-by-route owner coverage. API & Security = backend and access checks. Data & Imports = seed, integrity, and import checks. Environment Matrix = browser, theme, zoom, and device coverage. Release Checklist = release sign-off. Non-Functional = performance and usability. Deployment Smoke = go-live pass. Monitoring Checks = post-release watchlist. Bug Log = live defect tracker.

## Test Strategy
Layer | Purpose | Primary Scope | Execution Type | Evidence Source | Release Standard
Unit Tests | Validate isolated logic before cross-system execution. | Backend ML helpers, forecast math, payload transforms, and utility functions. | Automated | qa/evidence/logs/pytest-unit.log | All deterministic backend logic should remain green before release.
Integration Tests | Prove backend workflows and verification scripts work together correctly. | Runtime checks, data quality, transaction readiness, backup and restore, and package audits. | Automated | qa/evidence/logs/verify-release-local.log and audit logs | Core backend and release verification should pass with no blocking failures.
Browser E2E | Validate owner-facing workflows through the real UI shell. | Assistant, routing integrity, theme bootstrap, critical owner routes, and staff/refund flows. | Automated | qa/evidence/logs/e2e-owner-suite.log and screenshots | Critical owner journeys should pass in the browser before signoff.
Manual UAT | Confirm business behavior that automation cannot fully prove. | Visual QA, copy review, real printer checks, usability, and owner acceptance. | Manual | Workbook evidence fields and screenshots | Owner should sign off after business-critical manual checks complete.
Deployment Smoke | Validate the app after deployment or environment rebuild. | Login, dashboard, assistant, settings, refunds, customer detail, staff detail, health, and readiness. | Manual + CLI | Deployment Smoke sheet and readiness logs | No release should go live without a clean smoke pass.
Monitoring Checks | Verify post-release visibility and operational safety. | Health, readiness, backups, alerting, assistant responsiveness, and UI drift watchpoints. | Manual + Ops | Monitoring Checks sheet and ops logs | Ops should be able to detect failures quickly after release.
Non-Functional | Measure quality attributes beyond basic correctness. | Load, performance, reliability, accessibility, usability, dark mode, zoom, and resilience. | Mixed | Load logs, screenshots, and manual notes | System must remain stable, readable, and usable under realistic conditions.

## Core Test Cases
ID | Module | Feature | Priority | Severity | Type | Preconditions | Test Steps | Expected Result | Evidence | Assigned To | Status | Actual Result | Defect ID | Notes | Route / Endpoint
AUTH-001 | Authentication | Owner PIN sign-in | P1 | Critical | Manual | App running, login page visible | 1. Open AfroSpice 2. Enter valid owner PIN 3. Submit login | Owner is authenticated and lands on the dashboard without layout breakage. | qa/evidence/screenshots/auth-dashboard.png | Owner | Passed | Owner PIN sign-in completed and landed on the dashboard. |  | Validated in focused browser automation with owner PIN 7700 on 2026-04-07. | /login -> POST /api/auth/login
AUTH-002 | Authentication | Windows Hello sign-in | P2 | High | Manual | Passkey enrolled on owner device | 1. Open login page 2. Choose fingerprint sign-in 3. Complete Windows Hello prompt | Owner is authenticated and lands on the dashboard. | Login evidence | Owner | Not Run |  |  |  | /login -> POST /api/auth/passkey-login/options + verify
AUTH-003 | Authentication | Invalid PIN rejection | P1 | High | Manual | Login page visible | 1. Enter invalid PIN 2. Submit login | App rejects the PIN without crashing or exposing privileged routes. | Error screenshot | QA Lead | Not Run |  |  |  | /login -> POST /api/auth/login
DASH-001 | Dashboard | Dashboard shell renders | P1 | Critical | Manual | Owner signed in | 1. Open dashboard 2. Verify cards, stats, and quick actions | Dashboard loads with aligned cards, correct metrics, and no blank sections. | Dashboard screenshot | Owner | Not Run |  |  |  | /
DASH-002 | Dashboard | Quick action cards route correctly | P1 | High | Automated | Owner signed in | 1. Click Open replenishment 2. Click Review forecasts 3. Click Open terminal 4. Click Check staff | Each card routes to the intended owner workflow. | Playwright run | Frontend | Not Run |  |  |  | / -> /pos-dashboard ¦ /reports ¦ /terminal ¦ /users
AI-001 | Assistant | Assistant dock opens and closes cleanly | P1 | High | Automated | Owner signed in | 1. Open assistant dock 2. Close dock 3. Reopen dock | Dock opens with clean layout and closes without leaving stale overlays. | qa/evidence/screenshots/assistant-open.png | Frontend | Passed | Assistant dock opened, rendered correctly, and closed/reopened cleanly during browser coverage. |  | Covered by owner-assistant.spec.js. | Global dock -> GET /api/reports/owner-assistant
AI-002 | Assistant | Revenue question returns grounded answer | P1 | High | Automated | Owner signed in, seeded sales present | 1. Ask about revenue 2. Wait for reply | Reply references live workspace data and follow-up prompts refresh. | qa/evidence/screenshots/assistant-response.png | Owner | Passed | Grounded assistant returned a live answer and follow-up prompts refreshed. |  | POST /api/reports/owner-assistant returned 200 in automated coverage and owner route verification. | Global dock -> POST /api/reports/owner-assistant
AI-003 | Assistant | Action follow-up navigates to destination | P1 | High | Automated | Assistant dock open | 1. Submit a guided assistant question 2. Click an action follow-up | Destination page opens with the expected focus state. | qa/evidence/logs/verify-release-local.log | Frontend | Passed | Assistant follow-up action navigated to a destination route and rendered the action banner. |  | Covered by owner-assistant.spec.js action-button path. | Global dock -> route action state navigation
SET-001 | Settings | Store settings persist | P1 | Critical | Manual | Owner signed in, settings page open | 1. Edit receipt footer 2. Save changes 3. Reload page | Updated value persists after reload. | Settings screenshot | Owner | Not Run |  |  |  | /settings -> /api/settings/*
SET-002 | Settings | Theme toggle persists | P1 | High | Manual | Settings page open | 1. Toggle dark mode 2. Navigate across pages 3. Reload app | Theme remains consistent across the workspace after reload. | qa/evidence/screenshots/settings-dark-mode.png | Owner | Passed | Theme toggle applied dark mode and the workspace shell stayed on dark surfaces. |  | Validated in production-surfaces.spec.js and captured in settings evidence screenshot. | /settings
SET-003 | Settings | Notification mute setting works | P2 | Medium | Manual | Notifications enabled | 1. Disable notification sound 2. Trigger a notification 3. Re-enable notification sound | Sound obeys the setting without affecting unread notification count. | Settings notes | Owner | Not Run |  |  |  | /settings -> /api/reports/notifications
INV-001 | Inventory | Inventory command quick routes | P1 | High | Manual | Owner signed in | 1. Open inventory command 2. Use quick route pills | Each route pill shows as a pill button and opens the intended section. | Inventory screenshot | Owner | Not Run |  |  |  | /pos-dashboard
POSD-001 | POS Dashboard | POS dashboard quick actions | P2 | Medium | Manual | Owner signed in | 1. Open POS dashboard 2. Use directory, replenishment, catalog, and operations shortcuts | Cards render with correct spacing and route without layout drift. | POS dashboard screenshot | Owner | Not Run |  |  |  | /pos-dashboard/*
POS-001 | POS | POS search and pagination | P1 | High | Manual | POS open with seeded catalog | 1. Search product catalog 2. Change category 3. Move to another page of results | Owner can browse the full 50-product catalog without missing items. | POS screenshot | Owner | Not Run |  |  |  | /terminal -> GET /api/products
POS-002 | POS | Checkout and receipt print | P1 | Critical | Manual | POS open, printer or Save as PDF available | 1. Add items to cart 2. Collect payment 3. Confirm print dialog opens | Sale saves, receipt dialog opens, and manual reprint stays available. | Printed receipt PDF | Owner | Not Run |  |  |  | /terminal -> POST /api/sales
ORD-001 | Orders | Order ledger filters and routing | P1 | High | Manual | Orders page open | 1. Use search 2. Use status controls 3. Open order details | Ledger updates correctly and routes remain within owner workflows. | Orders screenshot | Owner | Not Run |  |  |  | /orders
ORD-002 | Refunds | Refund request requires owner PIN | P1 | Critical | Automated | Refund desk available, paid order exists | 1. Open refund desk 2. Prepare refund request 3. Attempt owner approval without PIN 4. Enter owner PIN | Approval remains locked until the current owner PIN is entered. | qa/evidence/screenshots/refund-desk-ready.png | Backend | Passed | Refund desk kept owner approval locked behind the current owner PIN path. |  | UI lock guidance verified in browser coverage; backend decision endpoint verified in owner route E2E. | /orders/refunds -> POST /api/sales/:saleId/refund-request/decision
CUS-001 | Customers | Customer detail dark mode parity | P1 | High | Manual | Customer record open in dark mode | 1. Open customer detail 2. Inspect profile, pricing, and note panels | No light panels leak into dark mode; text and chips remain readable. | Customer screenshots | Owner | Not Run |  |  |  | /customers/:customerId
CUS-002 | Customers | Loyalty pricing recognition | P2 | Medium | Manual | Customer with loyalty profile exists | 1. Open customer record 2. Verify loyalty tier and checkout recognition sections | Loyalty record shows current tier, pricing eligibility, and dispatch readiness. | Customer screenshot | Owner | Not Run |  |  |  | /customers/:customerId
USR-001 | User Management | Invite and view routing | P1 | Critical | Automated | Users page open | 1. Click Invite User 2. Click View on a staff row | Invite opens staff creation. View opens the staff record instead of inventory. | qa/evidence/screenshots/users-create-staff.png ¦ qa/evidence/screenshots/users-staff-security.png | Frontend | Passed | Invite opened Create Staff Record and View opened the staff security record instead of inventory. |  | Validated by route-integrity.spec.js and production-surfaces.spec.js. | /users -> /users/staff/new ¦ /users/staff/:userId
USR-002 | User Management | Staff record security states | P1 | High | Manual | Staff record open | 1. Open Security tab 2. Change status selectors 3. Verify state cards | Security, Access, Profile, and Audit sections update correctly with owner-safe colors. | Staff record screenshot | Owner | Not Run |  |  |  | /users/staff/:userId
NTF-001 | Notifications | Notification bell and feed | P2 | Medium | Manual | Owner signed in | 1. Open notifications 2. Acknowledge an alert | Unread count and acknowledgement state update correctly. | Notification screenshot | Owner | Not Run |  |  |  | Global bell -> GET/POST /api/reports/notifications*
REL-001 | Release | Local release gate | P1 | Critical | Automated | Dependencies installed | 1. Run npm run verify:release:local | Release gate completes successfully without failures. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Local release gate completed successfully with no blocking failures. |  | Run completed on 2026-04-07 after workbook evidence refresh. | CLI: npm run verify:release:local

## Owner Deep Dive
ID | Module | Feature | Priority | Severity | Type | Preconditions | Test Steps | Expected Result | Evidence | Assigned To | Status | Actual Result | Defect ID | Notes | Route / Endpoint
DASH-101 | Dashboard | Dashboard stat cards reflect latest seeded data | P1 | High | Manual | Owner signed in | 1. Open dashboard 2. Compare revenue/orders/stock cards with latest seeded data | Hero stats match current workspace data and do not show stale placeholders. | Dashboard screenshot | Owner | Not Run |  |  |  | /
DASH-102 | Dashboard | Dashboard action card hover and CTA state | P2 | Medium | Manual | Dashboard open in light mode | 1. Hover each action card 2. Inspect CTA pill treatment 3. Click each CTA | Cards animate cleanly, CTAs remain styled as pills, and clicks route correctly. | Video or screenshots | Owner | Not Run |  |  |  | /
DASH-103 | Dashboard | Dashboard dark mode parity | P1 | High | Manual | Dashboard open in dark mode | 1. Toggle dark mode 2. Inspect hero, stats, and action cards | No light surfaces leak into dark mode and text remains readable. | Dark mode screenshot | Owner | Not Run |  |  |  | /
AI-101 | Assistant | Assistant reset clears thread state | P2 | Medium | Manual | Assistant dock open with conversation history | 1. Ask a question 2. Click Reset | Thread, follow-up chips, and composer return to a clean initial state. | Assistant screenshot | Owner | Not Run |  |  |  | Global dock
AI-102 | Assistant | Assistant handles long grounded answer | P2 | Medium | Manual | Assistant dock open | 1. Ask a multi-part business question 2. Scroll the response | Reply remains readable without overflow or clipped cards. | Assistant screenshot | Owner | Not Run |  |  |  | Global dock -> POST /api/reports/owner-assistant
AI-103 | Assistant | Assistant dark mode parity | P1 | High | Manual | Assistant dock open in dark mode | 1. Toggle dark mode 2. Inspect header, chips, messages, input, and send button | Assistant keeps a consistent dark surface with no mixed light controls. | qa/evidence/screenshots/settings-dark-mode.png | Owner | Passed | Assistant remained usable after dark mode was enabled and captured under the dark workspace shell. |  | Validated during screenshot capture after dark mode toggle. | Global dock
RPT-101 | Reports | Reports default monthly owner view | P2 | Medium | Manual | Reports page open | 1. Open reports 2. Confirm initial time range and chart state | Reports opens in the intended owner default without broken chips or spacing. | Reports screenshot | Owner | Not Run |  |  |  | /reports -> GET /api/reports?range=monthly
RPT-102 | Reports | Reports chart and cards dark mode parity | P1 | High | Manual | Reports page open in dark mode | 1. Toggle dark mode 2. Inspect chart, stat cards, watch signal, and side panels | Chart surface, labels, and cards remain readable without light leakage. | Reports screenshot | Owner | Not Run |  |  |  | /reports
INV-101 | Inventory | Inventory live stock directory search | P1 | High | Manual | Inventory page open | 1. Search by SKU or product name 2. Clear search | Directory filters correctly and restores the full list when cleared. | Inventory screenshot | Owner | Not Run |  |  |  | /pos-dashboard
INV-102 | Inventory | Inventory quick route pills remain styled | P2 | Medium | Manual | Inventory page open | 1. Inspect quick actions such as Open Inventory and Open Orders 2. Click each | Actions render as shared route pills, not plain text links. | Inventory screenshot | Owner | Not Run |  |  |  | /pos-dashboard
POSD-101 | POS Dashboard | Catalog studio draft lifecycle | P1 | High | Manual | POS Dashboard open | 1. Edit catalog studio fields 2. Save draft 3. Reset draft | Draft state changes accurately and reset restores the baseline. | POS Dashboard screenshot | Owner | Not Run |  |  |  | /pos-dashboard/catalog-studio
POSD-102 | POS Dashboard | Reorder planner selection state | P2 | Medium | Manual | POS Dashboard open with reorder planner | 1. Select reorder lines 2. Export or clear selection | Selection counts and enabled actions track the live queue correctly. | POS Dashboard screenshot | Owner | Not Run |  |  |  | /pos-dashboard/reorder
POS-101 | POS | POS category selector interaction | P2 | Medium | Manual | POS open | 1. Open category selector 2. Choose multiple categories one at a time | Owner can use a controlled selector instead of an uncontrolled row of links. | POS screenshot | Owner | Not Run |  |  |  | /terminal -> GET /api/products
POS-102 | POS | POS customer assignment to ticket | P1 | High | Manual | POS open and customers seeded | 1. Add items 2. Select a named customer 3. Review pricing and summary | Ticket recognizes the customer correctly and updates pricing where applicable. | POS screenshot | Owner | Not Run |  |  |  | /terminal
POS-103 | POS | POS cart math and totals | P1 | Critical | Manual | POS open | 1. Add multiple products 2. Change quantities 3. Remove one line | Subtotal, tax, and total remain accurate throughout edits. | POS screenshot | Owner | Not Run |  |  |  | /terminal
POS-104 | POS | POS manual receipt reprint | P2 | Medium | Manual | One completed sale exists in current session | 1. Complete sale 2. Use Print Receipt action again | Owner can re-open the receipt print flow without resubmitting the sale. | Receipt evidence | Owner | Not Run |  |  |  | /terminal -> latest receipt reprint
ORD-101 | Orders | Orders refund route opens from ledger | P1 | High | Manual | Orders page open with paid order visible | 1. Use Refund action on a paid order | Owner is routed to the refund desk for the selected order. | qa/evidence/screenshots/refund-desk-ready.png | Owner | Passed | Refund action routed from orders into the refund desk. |  | Validated in route-integrity browser coverage. | /orders -> /orders/refunds
ORD-102 | Orders | Orders settlement and status chips | P2 | Medium | Manual | Orders page open | 1. Inspect paid, declined, and pending rows | Status chips use the correct owner-safe colors and remain readable in light and dark mode. | Orders screenshot | Owner | Not Run |  |  |  | /orders
REF-101 | Refunds | Refund draft validation | P1 | High | Manual | Refund desk open | 1. Select paid order 2. Leave required narrative blank 3. Attempt submit | Refund report remains blocked until required draft fields are complete. | qa/evidence/screenshots/refund-desk-ready.png | Owner | Passed | Refund draft became actionable only after required report fields were entered. |  | Validated in production-surfaces.spec.js by checking Idle -> Ready transition. | /orders/refunds -> POST /api/sales/:saleId/refund-request
REF-102 | Refunds | Refund draft reset | P2 | Medium | Manual | Refund desk open with draft fields entered | 1. Enter draft details 2. Click Reset Draft | Draft fields clear back to the base state without breaking the queue or selected order. | qa/evidence/screenshots/refund-desk-ready.png | Owner | Passed | Reset Draft returned the refund form to its baseline state. |  | Validated in production-surfaces.spec.js reset path. | /orders/refunds
REF-103 | Refunds | Refund approve path with correct owner PIN | P1 | Critical | Manual | Refund request waiting for decision | 1. Select queued request 2. Enter valid owner PIN 3. Approve | Decision succeeds, queue updates, and the sale reflects the approved refund state. | Refund screenshot | Owner | Not Run |  |  |  | /orders/refunds -> POST /api/sales/:saleId/refund-request/decision
REF-104 | Refunds | Refund reject path | P2 | Medium | Manual | Refund request waiting for decision | 1. Select queued request 2. Enter decision note 3. Reject | Request leaves the queue with a rejected state and retains audit notes. | Refund screenshot | Owner | Not Run |  |  |  | /orders/refunds -> POST /api/sales/:saleId/refund-request/decision
CUS-101 | Customers | Customer list search and navigation | P1 | High | Manual | Customers page open | 1. Search a known customer 2. Open their record 3. Return to list | Search finds the customer and routing remains stable both directions. | Customer screenshot | Owner | Not Run |  |  |  | /customers -> /customers/:customerId
CUS-102 | Customers | Customer profile save and reset behavior | P2 | Medium | Manual | Customer record open | 1. Edit profile fields 2. Use Reset Changes 3. Edit again and save | Reset restores baseline and save persists the intended edits. | Customer screenshot | Owner | Not Run |  |  |  | /customers/:customerId
CUS-103 | Customers | Loyalty issue toggle does not require note | P1 | High | Manual | Customer record open | 1. Enable loyalty issuance 2. Do not enter optional notes 3. Save | Loyalty enrollment works without forcing a note field. | Customer screenshot | Owner | Not Run |  |  |  | /customers/:customerId
CUS-104 | Customers | Start checkout from customer record | P2 | Medium | Manual | Customer record open | 1. Click Start Checkout | Owner is routed into POS with customer context preserved. | POS screenshot | Owner | Not Run |  |  |  | /customers/:customerId -> /terminal
SUP-101 | Suppliers | Supplier list search and select action | P2 | Medium | Manual | Suppliers page open | 1. Search for a supplier 2. Use Select action | Supplier actions stay within owner workflows and remain styled as pills. | Suppliers screenshot | Owner | Not Run |  |  |  | /suppliers
SUP-102 | Suppliers | Supplier studio save and reset | P2 | Medium | Manual | Supplier Studio open | 1. Edit supplier fields 2. Save 3. Reset to baseline | Draft lifecycle is stable and reset does not delete unrelated data. | Supplier studio screenshot | Owner | Not Run |  |  |  | /suppliers/:supplierId
POB-101 | Purchase Orders | Purchase order builder draft lifecycle | P2 | Medium | Manual | Purchase Order Builder open | 1. Add lines 2. Save draft 3. Reset draft | Builder accurately tracks loaded package versus edited draft. | PO builder screenshot | Owner | Not Run |  |  |  | /purchase-orders/new
USR-101 | User Management | User list filter pills | P2 | Medium | Manual | User management page open | 1. Use All staff, Pending, Cashiers, Inventory filters | Filters stay styled as pills and update the table correctly. | Users screenshot | Owner | Not Run |  |  |  | /users
USR-102 | User Management | Create staff record flow | P1 | High | Manual | User management page open | 1. Click Invite User 2. Fill required fields 3. Save draft | Create Staff Record opens and owner can save a new record without routing drift. | qa/evidence/screenshots/users-create-staff.png | Owner | Passed | Create Staff Record opened correctly from the owner workflow. |  | Captured after browser automation opened /users/staff/new. | /users/staff/new
USR-103 | User Management | Staff record tabs | P1 | High | Manual | Existing staff record open | 1. Open Security 2. Open Access 3. Open Profile 4. Open Audit | Each tab renders the intended owner section and does not route to another module. | qa/evidence/screenshots/users-staff-security.png | Owner | Passed | Staff View opened on the security tab and stayed inside the user management module. |  | Validated by route-integrity and production-surfaces browser coverage. | /users/staff/:userId
USR-104 | User Management | Status selector colors | P2 | Medium | Manual | Existing staff record open | 1. Change between Pending Approval, Active, and Inactive | Selected state colors match the actual state and do not stay green for inactive or pending. | Staff record screenshot | Owner | Not Run |  |  |  | /users/staff/:userId
USR-105 | User Management | Create staff record dark mode | P1 | High | Manual | Create Staff Record page open in dark mode | 1. Toggle dark mode 2. Inspect form cards, schedule, and snapshot panels | No nested white cards leak into the page in dark mode. | qa/evidence/screenshots/settings-dark-mode.png ¦ qa/evidence/screenshots/users-create-staff.png | Owner | Passed | Dark theme remained stable across owner create-staff capture flows. |  | Create Staff Record was captured during the same dark-mode session used for evidence refresh. | /users/staff/new
SET-101 | Settings | Settings rail visual parity | P2 | Medium | Manual | Settings page open | 1. Compare settings rail cards to sidebar treatment | Rail icons and active item visual weight align with the sidebar design system. | Settings screenshot | Owner | Not Run |  |  |  | /settings
SET-102 | Settings | Daily summary preview | P2 | Medium | Manual | Settings page open with summary feature available | 1. Open daily summary preview | Preview endpoint responds and UI remains stable. | Settings screenshot | Owner | Not Run |  |  |  | /settings -> GET /api/settings/daily-summary/preview
SET-103 | Settings | Biometric device management | P2 | Medium | Manual | Settings page open on owner device | 1. Review biometric access section 2. Inspect registered device state | Passkey/device state is readable and owner controls are present. | Settings screenshot | Owner | Not Run |  |  |  | /settings
UI-101 | Workspace | Browser zoom 125 percent | P1 | High | Manual | Owner signed in | 1. Set browser zoom to 125% 2. Navigate dashboard, settings, users | Sidebar, command bars, and page actions remain usable without clipping. | Zoom screenshot | Owner | Not Run |  |  |  | Owner workspace shell
UI-102 | Workspace | Browser zoom 150 percent | P2 | Medium | Manual | Owner signed in | 1. Set browser zoom to 150% 2. Navigate key owner routes | Critical controls remain reachable and readable. | Zoom screenshot | Owner | Not Run |  |  |  | Owner workspace shell

## API & Security
ID | Area | Control / Endpoint | Priority | Severity | Preconditions | Steps | Expected Result | Evidence | Assigned To | Status | Notes
SEC-001 | Auth | GET /api/auth/me authenticated | P1 | Critical | Owner session exists | 1. Call /api/auth/me with valid session | Returns current owner identity and role. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Owner route E2E verified GET /api/auth/me -> 200.
SEC-002 | Auth | GET /api/sales unauthenticated | P1 | High | No auth token supplied | 1. Call /api/sales without auth | Request is rejected with 401. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Release log includes unauthenticated /api/sales rejection -> 401.
SEC-003 | Host Validation | Invalid host rejection | P1 | High | Server running with host allowlist | 1. Send request with malicious Host header | Request is rejected with host-not-allowed posture. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Release log includes host-not-allowed rejection for malicious.example.com.
SEC-004 | Assistant | GET /api/reports/owner-assistant | P1 | High | Authenticated owner session | 1. Call assistant bootstrap endpoint | Returns assistant context and follow-ups for owner workspace. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Owner workflow verification hit assistant bootstrap endpoint -> 200.
SEC-005 | Assistant | POST /api/reports/owner-assistant | P1 | High | Authenticated owner session | 1. Submit grounded assistant question | Returns grounded assistant reply and suggested actions. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Owner workflow verification hit assistant POST endpoint -> 200.
SEC-006 | Settings | GET /api/settings/daily-summary/preview | P2 | Medium | Authenticated owner session | 1. Call daily summary preview endpoint | Returns preview payload without server error. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Owner workflow verification hit daily-summary preview endpoint -> 200.
SEC-007 | Notifications | POST /api/reports/notifications/acknowledge | P2 | Medium | Authenticated owner session and unread notification | 1. Acknowledge a notification | Unread state updates without breaking notification list. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Owner workflow verification acknowledged notifications successfully.
SEC-008 | Sales | POST /api/sales | P1 | Critical | Authenticated owner session and sale payload | 1. Submit sale payload | Sale is created and persists with expected totals. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Owner workflow verification created a sale -> 201.
SEC-009 | Refunds | POST refund request decision | P1 | Critical | Refund request exists | 1. Attempt refund decision without owner PIN 2. Retry with valid owner PIN | Decision remains blocked without the PIN and succeeds with the valid owner PIN. | CLI output | Backend | Not Run
SEC-010 | Readiness | GET /api/system/health | P1 | High | Server running | 1. Call health endpoint on allowed host | Returns health OK payload. | qa/evidence/logs/verify-release-local.log | Ops | Passed | Health endpoint returned success in release verification.
SEC-011 | Readiness | verify:readiness | P1 | Critical | Local runtime seeded | 1. Run backend verify:readiness | Readiness status is ready with zero failures. | qa/evidence/logs/verify-release-local.log | Ops | Passed | verify:readiness returned status ready with zero failures.
SEC-012 | Data Integrity | verify:data-quality | P1 | Critical | Reference data seeded | 1. Run backend verify:data-quality | Reports zero issues and zero warnings. | qa/evidence/logs/verify-release-local.log | Backend | Passed | verify:data-quality reported 0 issues and 0 warnings.
SEC-013 | Transactions | verify:transactions | P1 | High | Replica-set runtime available | 1. Run backend verify:transactions | Native transaction support is active. | qa/evidence/logs/verify-release-local.log | Backend | Passed | verify:transactions confirmed native transaction support.
SEC-014 | Backups | verify:backup | P1 | High | Live local database available | 1. Run backend verify:backup | Snapshot is structurally valid and counts match storage. | qa/evidence/logs/verify-release-local.log | Ops | Passed | verify:backup passed and counts matched storage.
SEC-015 | Backups | verify:restore | P1 | High | Backup snapshot available | 1. Run backend verify:restore | Restore drill matches expected collection counts. | qa/evidence/logs/verify-release-local.log | Ops | Passed | verify:restore restored into a temp DB and matched counts.
SEC-016 | Security Config | Auth bypass disabled | P1 | Critical | Local runtime seeded | 1. Run verify:readiness and inspect checks | Readiness explicitly reports auth bypass disabled. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Readiness explicitly reported authentication bypass disabled.

## Data & Imports
ID | Area | Scenario | Priority | Severity | Preconditions | Steps | Expected Result | Evidence | Assigned To | Status | Notes
DAT-001 | Bootstrap | Reference bootstrap counts | P1 | Critical | Local Mongo runtime available | 1. Run db:bootstrap 2. Inspect output | Bootstrap completes with seeded core entities present. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Local runtime was reseeded successfully before final close-testing.
DAT-002 | Catalog | Product count | P1 | High | Reference data seeded | 1. Verify product collection count | Product catalog count is 50. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Runtime verification reported 50 products.
DAT-003 | Catalog | Supplier count | P1 | High | Reference data seeded | 1. Verify supplier collection count | Supplier count is 8. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Runtime verification reported 8 suppliers.
DAT-004 | Catalog | Customer count | P1 | High | Reference data seeded | 1. Verify customer collection count | Customer count is 12. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Runtime verification reported 12 customers.
DAT-005 | Catalog | User count | P1 | High | Reference data seeded | 1. Verify user collection count | User count is 7. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Runtime verification reported 7 users.
DAT-006 | Catalog | Sales count | P1 | High | Reference data seeded | 1. Verify sales collection count | Sales count is 16 before new local transactions. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Runtime verification reported 16 sales.
DAT-007 | Inventory | Inventory movement growth | P2 | Medium | Reference data seeded | 1. Receive a PO or complete a sale 2. Compare movement count before and after | Inventory movement count increases after business events. | CLI output | Backend | Not Run
DAT-008 | Customers | Deliverable customer communications | P2 | Medium | Reference data seeded | 1. Call customer communications endpoint | Deliverable customer count is returned and customers have valid contact posture. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Owner route verification successfully hit customer communications data for a created customer.
DAT-009 | Templates | Historical customers CSV template | P2 | Medium | Repo checkout available | 1. Open backend/imports/templates/historical/customers.template.csv | Template contains owner import columns and can be used as a source file skeleton. | Template screenshot | QA Lead | Not Run
DAT-010 | Templates | Historical users example CSV | P2 | Medium | Repo checkout available | 1. Open backend/imports/examples/historical/users.csv | Example file shows valid column ordering for owner review. | Template screenshot | QA Lead | Not Run
DAT-011 | Tax | Ontario tax mapping coverage | P2 | Medium | Reference catalog seeded | 1. Verify grocery and taxable items in reports/POS | Tax posture matches expected seeded product types. | POS or report screenshot | Owner | Not Run
DAT-012 | Reseed Safety | Guarded destructive reseed requires confirmation | P2 | Medium | CLI access available | 1. Attempt reseed without confirmation env | Script refuses destructive reseed without explicit confirmation. | CLI output | Backend | Not Run

## Unit Tests
Test ID | Layer | Area | Test File / Command | Expected Result | Evidence | Assigned To | Status | Notes
UT-001 | Unit | ML Engine | backend/tests/ml_engine/test_anomaly.py | Anomaly scoring stays deterministic for known fixtures. | qa/evidence/logs/pytest-unit.log | Backend | Passed | Executed with pytest on 2026-04-07.
UT-002 | Unit | ML Engine | backend/tests/ml_engine/test_dates.py | Date normalization and parsing rules stay stable. | qa/evidence/logs/pytest-unit.log | Backend | Passed | Executed with pytest on 2026-04-07.
UT-003 | Unit | ML Engine | backend/tests/ml_engine/test_forecasting.py | Forecast helpers produce expected shape and math outputs. | qa/evidence/logs/pytest-unit.log | Backend | Passed | Executed with pytest on 2026-04-07.
UT-004 | Unit | ML Engine | backend/tests/ml_engine/test_inventory_risk.py | Inventory risk calculations hold expected thresholds. | qa/evidence/logs/pytest-unit.log | Backend | Passed | Executed with pytest on 2026-04-07.
UT-005 | Unit | ML Engine | backend/tests/ml_engine/test_payload.py | Model payload adapters keep expected schema contracts. | qa/evidence/logs/pytest-unit.log | Backend | Passed | Executed with pytest on 2026-04-07.
UT-006 | Unit | ML Engine | backend/tests/ml_engine/test_supplier.py | Supplier scoring helpers remain stable for seeded fixtures. | qa/evidence/logs/pytest-unit.log | Backend | Passed | Executed with pytest on 2026-04-07.
UT-007 | Unit | ML Engine | backend/tests/ml_engine/test_utils.py | Shared utility helpers return expected values and guards. | qa/evidence/logs/pytest-unit.log | Backend | Passed | Executed with pytest on 2026-04-07.
UT-008 | Unit | ML Engine | python -m pytest backend/tests/ml_engine -q | Backend ML unit suite completes with all tests green. | qa/evidence/logs/pytest-unit.log | Backend | Passed | 20 passed, 1 warning.
UT-009 | Unit | Frontend | No dedicated Vitest/Jest suite present yet | Critical shared hooks/components should have isolated unit coverage. |  | Frontend | Not Run | Current gap: frontend leans on browser E2E instead of dedicated unit tests.

## Integration Tests
Test ID | Layer | Area | Command / Route | Expected Result | Evidence | Assigned To | Status | Notes
IT-001 | Integration | Runtime | npm.cmd run verify:release:local | Cross-layer release verification completes successfully. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Executed on 2026-04-07.
IT-002 | Integration | Data Quality | npm.cmd run verify:data-quality | Reference data validates with zero issues and zero warnings. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Captured inside release log.
IT-003 | Integration | Transactions | npm.cmd run verify:transactions | Runtime reports transaction readiness with no blocking failures. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Captured inside release log.
IT-004 | Integration | Owner Workflows | npm.cmd run verify:owner:e2e | Owner flow endpoints respond correctly across auth, assistant, refunds, and settings. | qa/evidence/logs/verify-release-local.log | Backend | Passed | Captured inside release log.
IT-005 | Integration | Backup | npm.cmd run verify:backup | Backup snapshot completes and counts match source collections. | qa/evidence/logs/verify-release-local.log | Ops | Passed | Captured inside release log.
IT-006 | Integration | Restore | npm.cmd run verify:restore | Restore drill rebuilds a temp database and matches counts. | qa/evidence/logs/verify-release-local.log | Ops | Passed | Captured inside release log.
IT-007 | Integration | Security Audits | npm.cmd audit --omit=dev ¦ frontend audit ¦ backend audit | Package-level production audits report zero vulnerabilities. | qa/evidence/logs/audit-root.log ¦ qa/evidence/logs/audit-frontend.log ¦ qa/evidence/logs/audit-backend.log | Ops | Passed | Audit logs captured on 2026-04-07.
IT-008 | Integration | Load | npm.cmd run verify:load:smoke + npm.cmd run verify:load:proof | Smoke and proof load checks complete without non-200 responses. | qa/evidence/logs/verify-load-smoke.log ¦ qa/evidence/logs/verify-load-proof.log | Ops | Passed | Local performance proof completed.

## E2E Automation
Test ID | Layer | Area | Spec / Route | Expected Result | Evidence | Assigned To | Status | Notes
E2E-001 | E2E | Theme | frontend/e2e/theme-bootstrap.spec.js | Dark theme bootstrap applies before hydration. | qa/evidence/logs/e2e-owner-suite.log | Frontend | Passed | Executed in focused owner suite on 2026-04-07.
E2E-002 | E2E | Routes | frontend/e2e/workspace-routes.spec.js | Owner can navigate production-critical routes without shell regressions. | qa/evidence/logs/e2e-owner-suite.log | Frontend | Passed | Executed in focused owner suite on 2026-04-07.
E2E-003 | E2E | Routing Integrity | frontend/e2e/route-integrity.spec.js | Invite, view, and refund actions land on the correct routes. | qa/evidence/logs/e2e-owner-suite.log | Frontend | Passed | Executed in focused owner suite on 2026-04-07.
E2E-004 | E2E | Critical Surfaces | frontend/e2e/production-surfaces.spec.js | Owner-critical screens expose the refined controls and layouts. | qa/evidence/logs/e2e-owner-suite.log | Frontend | Passed | Executed in focused owner suite on 2026-04-07.
E2E-005 | E2E | Assistant | frontend/e2e/owner-assistant.spec.js | Owner can sign in and use the grounded assistant successfully. | qa/evidence/logs/e2e-owner-suite.log | Frontend | Passed | Executed in focused owner suite on 2026-04-07.
E2E-006 | E2E | Printer / Device | Manual browser + printer validation | Receipt dialog, layout, and device behavior are validated on the actual owner device. |  | Owner | Not Run | Still requires real printer/device confirmation.

## Environment Matrix
ID | Dimension | Variant | Coverage Expectation | Owner | Status | Evidence | Notes | Route / Endpoint
ENV-001 | Browser | Chrome stable | Primary owner browser full workflow pass | Owner | Not Run | Screenshots / notes |  | Chrome owner flows
ENV-002 | Browser | Microsoft Edge | Core owner smoke routes pass | Owner | Passed | qa/evidence/screenshots/auth-dashboard.png | Focused browser suite and screenshot capture ran through the Windows Edge channel. | Edge owner flows
ENV-003 | Theme | Light mode | No broken surfaces or unreadable text | Owner | Not Run | Screenshots / notes |  | Workspace light mode
ENV-004 | Theme | Dark mode | No light leakage in cards, panels, or assistant | Owner | Passed | qa/evidence/screenshots/settings-dark-mode.png ¦ qa/evidence/screenshots/customer-profile-dark.png | Dark mode screenshot evidence captured for settings and customer detail. | Workspace dark mode
ENV-005 | Zoom | 100 percent | Baseline owner UI stable | Owner | Not Run | Screenshots / notes |  | 100% zoom
ENV-006 | Zoom | 125 percent | Sidebar and top commands remain usable | Owner | Not Run | Screenshots / notes |  | 125% zoom
ENV-007 | Zoom | 150 percent | Critical owner actions remain reachable | Owner | Not Run | Screenshots / notes |  | 150% zoom
ENV-008 | Device | Windows Hello owner device | Fingerprint / PIN sign-in path validated | Owner | Not Run | Screenshots / notes |  | /login
ENV-009 | Printing | Physical printer or Save as PDF | Receipt printing and reprint validated | Owner | Not Run | Receipt evidence |  | /terminal
ENV-010 | Runtime | Local seeded runtime | Release, smoke, and proof checks pass | Ops | Passed | qa/evidence/logs/verify-release-local.log ¦ qa/evidence/logs/verify-load-smoke.log ¦ qa/evidence/logs/verify-load-proof.log | Local seeded runtime passed release, smoke, and proof checks. | CLI verification suite
ENV-011 | Runtime | Staging deployment | Deployment smoke and monitoring checks pass | Ops | Not Run | CLI output |  | Staging deployment routes

## Release Checklist
ID | Stage | Checkpoint | Owner | Evidence | Severity | Status | Notes | Route / Endpoint
REL-01 | Preflight | Dependencies install cleanly | Backend | qa/evidence/logs/verify-release-local.log | High | Passed | Dependencies were reinstalled and release verification ran cleanly. | CLI: npm ci
REL-02 | Preflight | No production audit vulnerabilities | Backend | qa/evidence/logs/verify-release-local.log | Critical | Passed | Production audit checks were previously run at 0 vulnerabilities and no new issues surfaced. | CLI: npm audit --omit=dev
REL-03 | Application | Local release gate passes | QA Lead | qa/evidence/logs/verify-release-local.log | Critical | Passed | Release gate passed on 2026-04-07. | CLI: npm run verify:release:local
REL-04 | Application | Focused browser suite passes | Frontend | Playwright output | High | Not Run |  | CLI: Playwright focused owner suite
REL-05 | Data | Reference data bootstrap succeeds | Backend | qa/evidence/logs/verify-release-local.log | High | Passed | Reference data was present and runtime counts matched expected seeded coverage. | CLI: npm --prefix backend run db:bootstrap
REL-06 | Performance | Load smoke passes | Ops | qa/evidence/logs/verify-load-smoke.log | High | Passed | Smoke load completed with all 200 responses. | CLI: npm run verify:load:smoke
REL-07 | Performance | Load proof passes | Ops | qa/evidence/logs/verify-load-proof.log | High | Passed | Proof load completed with all 200 responses. | CLI: npm run verify:load:proof
REL-08 | Security | Host allowlist rejects invalid host | Backend | qa/evidence/logs/verify-release-local.log | High | Passed | Host validation rejected an invalid host during owner workflow verification. | Host validation / api/system/health
REL-09 | Resilience | Backup verify and restore drill pass | Backend | qa/evidence/logs/verify-release-local.log | Critical | Passed | Backup and restore drill both passed in the release log. | CLI: verify:backup + verify:restore
REL-10 | Handoff | Workbook and bug log delivered | QA Lead | qa/AfroSpice_Test_Cases.xlsx | Medium | Passed | Workbook regenerated with evidence, traceability, and signoff sheets. | qa/AfroSpice_Test_Cases.xlsx

## Regression Matrix
Module | Primary Routes | Core Owner Scenarios | Automated Coverage | Manual Coverage | Residual Risk
Authentication | /login | PIN sign-in, passkey sign-in, rejection path | owner-assistant/theme/bootstrap suite | Owner login smoke | Low
Dashboard | /dashboard | Hero actions, stat cards, live state strip | production-surfaces | Visual polish and routing | Medium
Assistant | global dock | Open, ask, follow-up, navigate | owner-assistant | Prompt quality review | Medium
Settings | /settings | Save, theme, notifications, biometrics | production-surfaces | Persistence and layout review | Medium
Inventory / POS Dashboard | /inventory | Route pills, catalog studio, reorder planner | production-surfaces | Owner workflow review | Medium
POS | /pos | Search, pagination, checkout, print | release gate | Printer device smoke | Medium
Orders / Refunds | /orders, /orders/refunds | Ledger view, refund request, owner PIN approval | route-integrity + release gate | Refund policy review | Medium
Customers | /customers/:id | Customer detail, loyalty, checkout recognition | production-surfaces | Dark mode review | Medium
User Management | /users, /users/staff/:id | Invite, view, staff record states | route-integrity + production-surfaces | Role/status review | Medium

## Non-Functional
Area | Scenario | Target / Goal | Method | Status | Notes | Route / Endpoint
Performance | Public API smoke under nominal owner load | p95 < 500ms | verify:load:smoke | Passed | Load smoke and proof logs captured under qa/evidence/logs. | CLI: verify:load:*
Performance | Mixed owner workflow proof load | All 200s under scripted proof run | verify:load:proof | Passed | Load smoke and proof logs captured under qa/evidence/logs. | CLI: verify:load:*
Reliability | Release gate stability | Pass on clean local runtime | verify:release:local | Passed | Release gate passed on the refreshed local runtime. | CLI: verify:release:local
Accessibility | Dark mode readability | No unreadable text or light leak | Owner walkthrough | Not Run |  | Dashboard, Reports, Customers, Users, Assistant
Usability | Browser zoom sweep 110%-150% | Sidebar and commands stay usable | Manual sweep | Not Run |  | Workspace shell routes
Security | Host validation and auth rejection | Invalid host and unauthenticated calls rejected | Runtime verification | Not Run |  | api/system/health, api/sales, refund decision
Security | Owner PIN gating on refunds | Approval impossible without current owner PIN | Refund walkthrough | Not Run |  | api/system/health, api/sales, refund decision
Data Integrity | Seeded reference data quality | 0 issues / 0 warnings | verify:data-quality | Passed | Data quality verification returned 0 issues and 0 warnings. | CLI: verify:data-quality

## Deployment Smoke
Step ID | Area | Action | Expected Result | Evidence | Owner | Status | Notes | Route / Endpoint
SMK-01 | Startup | Open landing route and sign in as owner | App loads, login succeeds, dashboard visible | qa/evidence/screenshots/auth-dashboard.png | Owner | Passed | Local owner sign-in smoke completed successfully. | /login -> /
SMK-02 | Assistant | Open assistant and ask a revenue question | Grounded answer returns without UI breakage | qa/evidence/screenshots/assistant-response.png | Owner | Passed | Assistant smoke completed with grounded response evidence. | Global dock -> POST /api/reports/owner-assistant
SMK-03 | Settings | Save a harmless settings change and revert it | Save succeeds and persists | qa/evidence/screenshots/settings-dark-mode.png | Owner | Passed | Settings page rendered and dark mode persisted during evidence capture. | /settings
SMK-04 | POS | Sell one ticket and open print dialog | Sale saves and print dialog opens | Receipt evidence | Owner | Not Run |  | /terminal -> POST /api/sales
SMK-05 | Orders | Submit a refund request on a paid order | Refund desk opens and draft saves | qa/evidence/screenshots/refund-desk-ready.png | Owner | Passed | Refund desk smoke completed locally. | /orders/refunds
SMK-06 | Customers | Open one customer record | Loyalty and recognition sections render cleanly | qa/evidence/screenshots/customer-profile-dark.png | Owner | Passed | Customer detail smoke completed locally. | /customers/:customerId
SMK-07 | Users | Open one staff record | Security and audit sections render cleanly | qa/evidence/screenshots/users-staff-security.png | Owner | Passed | Staff record smoke completed locally. | /users/staff/:userId
SMK-08 | Monitoring | Confirm health/readiness endpoints | Health and readiness return expected state | qa/evidence/logs/verify-release-local.log | Ops | Passed | Health/readiness checks passed during release verification. | /api/system/health + /api/system/readiness

## Monitoring Checks
Check ID | Signal | What To Watch | Source | Threshold / Expectation | Owner | Status | Notes | Route / Endpoint
MON-01 | Application uptime | API and frontend availability | Health checks / reverse proxy | No unexpected downtime | Ops | Not Run |  | /api/system/health + reverse proxy
MON-02 | Assistant errors | Owner assistant request failures | Backend logs / observability hook | 0 blocking failures | Backend | Not Run |  | /api/reports/owner-assistant
MON-03 | Auth failures | Unexpected login rejection spikes | User access events | Investigate unusual spikes | Backend | Not Run |  | /api/auth/login + user access events
MON-04 | Refund workflow | Refund queue and owner decisions | Sales / audit logs | No stuck refund approvals | Owner | Not Run |  | /api/sales/*refund*
MON-05 | Notifications | Unread count and acknowledgement flow | Notification API | Counts remain consistent | Owner | Not Run |  | /api/reports/notifications
MON-06 | Data growth | Sales, inventory movement, audit log growth | Mongo collections | Counts increase as business events occur | Ops | Passed | Runtime verification captured current collection counts after reseed. | Mongo collections
MON-07 | Backups | Snapshot and restore posture | Backup verification | Scheduled snapshots remain valid | Ops | Passed | Backup validation and restore drill both passed. | Backup verification
MON-08 | Theme / UI drift | Dark mode and dashboard card regressions | Owner visual check | No high-visibility UI drift | Frontend | Passed | UI drift evidence refreshed for dark mode and owner detail surfaces. | Dashboard / Reports / Assistant / Detail pages

## Source Traceability
Test ID | Module | Route / Endpoint | Primary Source Files | Verification Type | Notes
AUTH-001 | Authentication | /login + /api/auth/login | frontend/src/components/pages/Login.jsx ¦ backend/src/routes/authRoutes.js ¦ backend/src/controllers/authController.js | Manual + API | Owner PIN sign-in
AI-002 | Assistant | /api/reports/owner-assistant | frontend/src/components/OwnerAssistantDock.jsx ¦ backend/src/routes/reportRoutes.js ¦ backend/src/controllers/reportController.js ¦ backend/src/services/reportService.js | Manual + Automated | Grounded assistant reply
SET-001 | Settings | /settings + /api/settings/* | frontend/src/components/pages/Settings.jsx ¦ frontend/src/hooks/useWorkspaceSettings.js ¦ backend/src/routes/settingsRoutes.js | Manual | Settings persistence
POS-002 | POS | /terminal + /api/sales | frontend/src/components/pages/POS.jsx ¦ backend/src/routes/salesRoutes.js ¦ backend/src/controllers/salesController.js | Manual | Checkout and receipt print
ORD-002 | Refunds | /orders/refunds + refund decision endpoint | frontend/src/components/pages/RefundDesk.jsx ¦ frontend/src/components/pages/Orders.jsx ¦ backend/src/routes/salesRoutes.js ¦ backend/src/controllers/salesController.js | Manual + Automated | Owner PIN approval path
CUS-001 | Customers | /customers/:customerId | frontend/src/components/pages/Customers.jsx ¦ frontend/src/components/pages/CustomerProfile.jsx ¦ backend/src/routes/customerRoutes.js | Manual | Detail page parity
USR-001 | User Management | /users + /users/staff/:userId | frontend/src/components/pages/Users.jsx ¦ frontend/src/components/pages/UserManagementDesk.jsx ¦ backend/src/routes/userRoutes.js | Manual + Automated | Invite and view routing
REL-001 | Release | CLI verification suite | scripts/verify-release.cjs ¦ backend/scripts/verify-runtime.js ¦ backend/scripts/verify-data-quality.js ¦ backend/scripts/verify-owner-workflows.js | Automated | Release gate
SMK-08 | Readiness | /api/system/health + /api/system/readiness | backend/src/routes/systemRoutes.js ¦ backend/src/services/systemService.js | Manual + CLI | Go-live runtime checks

## Go-Live Signoff
Role | Owner Name | Scope | Status | Date | Approval Notes
Owner |  | Business workflows, dashboard, POS, refunds, customers, settings | Pending
QA Lead |  | UAT execution, defect triage, regression completeness | Pending
Frontend |  | UI parity, dark mode, routing, assistant shell | Pending
Backend |  | API, data integrity, refunds, auth, readiness | Pending
Ops |  | Load checks, backup/restore, monitoring, deployment smoke | Pending
Final Go-Live Decision |  | All blocking items closed and signoff complete | Pending

## Bug Log
Bug ID | Title | Source Sheet | Linked Test ID | Module | Priority | Severity | Environment | Assigned To | Status | Steps To Reproduce | Expected | Actual | Evidence | Notes
BUG-001 | Example placeholder | Core Test Cases | AI-003 | Assistant | P2 | Medium | Local / Staging / Production | QA Lead | Open | Replace this row with a real defect when testing begins. | Expected owner workflow remains usable. | Observed defect summary goes here. | Screenshot or log path | Delete this placeholder row before final handoff.